## Sheet1
ID | Start time | Completion time | Email | Name | choose system code | 1000 Ship general design | 3000 Hull | 4000 Interrior | 5000 HVAC | 6000 Propulsion | 7000 Machinery | 8000 Deck | 9000 Electric | Are you satisfied with the technical output and choises of the system? | Rules requirements : Easy/hard? Everything fulfilled? Issues with class worth mentioning? | Material (purchase, logistics, budget) : Your experience and feedback? | Drawings (schedule, comments received, changes..) : Lessons learned? | Communication (internal and external), Co-operation with different parties (In own team, other design teams, subcontractors, production, suppliers, TK.. ) | Comparison to NB516-517 - did we learn? | Other comments?
4 | 2023-05-09 10:51 | 2023-05-09 11:00 | isko.kuha@helsinkishipyard.fi | Isko Kuha | 6000 |  |  |  |  | 6310 Propeller and shaftline; |  |  |  | Satisfied to 75%. We were able to improve from the "cousin ships" NB:s 516 and 517. But not all space-related issues in the aft bottom were available to change. We learned a lot. | The co-operation with Class LR was top professional and very well remembered. | Our small purchases for mounting parts was made difficult by payment reputation of ours. Also the delivery lead times of many materials and parts was long. | For some reason, my own personal contact with Owners' responsible inspectors was ultimately close to zero. This is a change when compared to past ship series. Perhaps the Covid pandemy had a part in the circumstance. Many "ping-pong" correspondance could have been dealt with up front in a more old-fashioned way. This was frustrating in many instances and communication was not always to the exact problem point. | See point 6 for Owners. Internal and contractor communication was generally excellent. However, the main system integrating supplier was obviously overworked in their projecting contracts and we could not bring basic design communication to a great level at all. | We certainly learned a lot. Especially in working together with Hull Design vs. Machinery Design.
5 | 2023-05-09 11:00 | 2023-05-09 11:02 | isko.kuha@helsinkishipyard.fi | Isko Kuha | 8000 | [6 empty] | 8210 Steering Gear Piping Diagram; |  | 90% happy. However, the main system integrating supplier was obviously overworked in their projecting contracts. | The co-operation with Class LR was top professional and very well remembered. | Our small purchases for mounting parts was made difficult by payment reputation of ours. Also the delivery lead times of many materials and parts was long. | Generally no complaints. | Was good. | This system had been succesfully implemented already in NB:s 516 and 517.
6 | 2023-05-09 11:03 | 2023-05-09 11:04 | isko.kuha@helsinkishipyard.fi | Isko Kuha | 8000 | [6 empty] | 8240 Tunnel Thruster Piping Diagram; |  | Yes, 100% happy. | The co-operation with Class LR was top professional and very well remembered. | Our small purchases for mounting parts was made difficult by payment reputation of ours. Also the delivery lead times of many materials and parts was long. | Was OK. | Was good indeed. | We were okay already in NB:s 516, 517.
7 | 2023-05-09 11:04 | 2023-05-09 11:06 | isko.kuha@helsinkishipyard.fi | Isko Kuha | 8000 | [6 empty] | 8310 Fin Stabiliser Piping Diagram; |  | 100% happy. The system supplier (Mitsubishi Heavy Industries) performed extremely well in the project. | The co-operation with Class LR was top professional and very well remembered. | Our small purchases for mounting parts was made difficult by payment reputation of ours. Also the delivery lead times of many materials and parts was long. | Was OK. | Generally very good co-operation and special thanks to production foremen and -women. | We improved the system implementation significantly when compared to NB:s 516 and 517.
8 | 2023-05-09 11:06 | 2023-05-09 11:09 | isko.kuha@helsinkishipyard.fi | Isko Kuha | 9000 | [7 empty] | 9311 Integrated Automation System (IAS); | I helped with IAS interfaces and it was nice. | The co-operation with Class LR was top professional and very well remembered. | Our small purchases for mounting parts was made difficult by payment reputation of ours. Also the delivery lead times of many materials and parts was long. | Was good. | Pleasant and efficient co-operation in spite of the very heavy workload of the good electrical design colleagues. | Was OK.
10 | 2023-05-09 10:29 | 2023-05-09 12:54 | jyrki.nurmi@helsinkishipyard.fi | Jyrki Nurmi | 9000 | [7 empty] | 9200 Lighting; | I am satisfied with the final output despite the restrictions and drawbacks caused by international sanctions. | Rule requirements did not cause problems. No issues with Class nor with Flag Rules | We had 2 issues that had an impact on material availability and affected the initial budget. #1 - Rising costs due to the global shortage of semiconductors had a negative impact during an ongoing project. Something not easy to foresee. #2 - International sanctions struck badly the normal, well-known material supplier chain. Time-consuming efforts had to be performed to fix the issues. | Wrong decisions were made at the beginning of the project. A reliable TK-contractor that had built the Passenger Public areas in 2 previous vessels was put aside and an incompetent contractor was chosen to work on the last vessel of the series. This was the worst action I have ever seen in my 30+ years working at the Yard. My first reaction was that the Yard was digging its own grave. First dismay came when we learned that the electrical design work was omitted from the contract. That was a huge red flag. The contractor had no responsible designer for the task. The Yard did not have the capacity to handle the work with its own personnel but had to hire a company from Croatia - on behalf of the TK-contractor, and for the TK-contractor. It was emphasized that this Croatian company is working for the TK-contractor, and they had to coordinate the design work with them (not the Yard). This never happened. The Yard had to teach the Croatians nearly everything. After the initial design work was done, the Croatians retired from their responsibilities, as it was stated in their contract. There was no-one responsible for the follow-ups and the changes that always come up during the building phase. I hope the costs of the extra tasks were estimated/calculated by the project's lead decision makers. Lessons to be learned: #1 - The first and paramount lesson is that a TK-contractor MUST have their own electrical designer(s) who is(are) responsible for the electrical design of the TK areas during the whole project - from the start to the end. #2 - The second lesson is that it is never a good idea to change a TK-contractor during a building series of vessels. There will doubtfully be any savings. | Communication depended a lot on your own activity. In my opinion communication has improved between team workers, production, and suppliers. This last TK-contractor was the worst case during my career at the Yard's design dpt. , although they had individual on-site supervisors among their personnel that understood the issues and could commendably tackle them. A light amid the darkness. | The 2 first vessels were difficult, but the last one feels like a total mess because of the new TK. As stated earlier, it is a very risky idea to change a competent contractor in the middle of a building series. The building areas under the responsibility of the Yard have gone with no issues and can be regarded as successful. | I sincerely hope that the above-mentioned mistakes will never occur again. This Shipyard has built many vessels with success, and I believe that the decades long trend will continue if lessons are learned. The cheapest is never the best nor will it turn out to be cheap in the end.
11 | 2023-05-09 12:02 | 2023-05-09 13:03 | juuso.pihl@helsinkishipyard.fi | Juuso Pihl | 9000 | [7 empty] | 9121 Transformers;9125 UPS Units;9132 Main Switchboards (MS11_MS12_MS21_MS22);9133 Emergency Switchboards (ES1_ES2_ES3);9134 Distribution Boards (PB_LB_HB_OB_etc.);9135 Motor Starter Units and Separate Starters;9137 Power Socket Units;9671 Information and audio-visual systems;9661 Data Network;9631 Central Antenna System;9621 Public Addressing System;9616 UHF Radio System;9613 Automatic Telephone System;9612 Talk Back Telephone System;9611 Sound Powered Telephone System; | Mostly | Nothing special to mention | 91xx Went well, some minor budget challenges 96xx Material logistic was big mess. Delivery registration missing. Missing equipment - TK suppliers has no responsibility of any material | Mostly ok. | Internal communication ok. External communication with suppliers mostly ok. Communication with 'the' TK supplier was bit challenging... | Some things went to correct direction but regarding TK the opposite way.
12 | 2023-05-09 10:36 | 2023-05-09 14:18 | Rando.Rosenthal@helsinkishipyard.fi | Rando Rosenthal | 8000 | [6 empty] | 8521 ports in shell plating;8522 Access and service hatches with handrails;8580 Outside Hull Outfitting and hull marking;8910 Tarpaulins and Covers;8510 Water Tight Doors;8710 Deck Stores and Workshops;8545 Windscreens, awnings and balcony dividers;8542 Exterior Railings;8541 Exterior Stairs and Ladders;8000 Deck Areas;8110 Anchoring and Mooring; |  | Way too many systems but fortunately most systems same as in previous vessels. It was more like coordinating in case of changes/modifications. Very satisfied to technical output except with watertight doors. Especially integration with SWT and fire doors. | More-less straight forward. Only Panama arrangement not fulfilled due to aft ship design. Tendering arrangement required more effort to understand which rules and requirement need to be filled. Otherwise no issues. | I consider material handling quite smooth. Mostly because it was already third vessel. Some late purchases had to made due to lost/broken equipment but this was managed in time. Delayed purchase of tender boat and davits also delayed design, delivery and installation (including late payments). | Block manufacturing timetable and detail design areas could have been more in line to give extra time for design. New equipment or supplier changing delayed detail design in some area (life - and tender boats). Some comments needed more clarification but mostly only minor changes in NB-518. | In my opinion communication was smooth between different parties. In late stage it was more hectic in some cases. | We got us well employed by changing the hull structure, suppliers and sub-contractors in third vessel.
13 | 2023-05-09 15:01 | 2023-05-09 15:16 | juri.huuhtanen@helsinkishipyard.fi | Juri Huuhtanen | 1000 | 1150 Design Criteria;1110 Ship Description; | [7 empty] | Yes. My systems are important for the other disciplines as guideline drawings for further detail design as well as important drawings for ship safety in general | Rules requirements seems to have been reasonable from my point of view. However, I inherited most of the system responsibilities and therefore did not experience all the difficulties related to my systems in early design phases. | My systems did not include material as such. | Some lessons learned to be mentioned (and corrective action done preferably already in concept phase): - Try not to position crew cabins (or any other cabins) adjacent to bow thruster spaces - Observation lounge and discotheque position below cabin spaces and bridge should be avoided or some special solutions should be applied to prevent noise and comfort issues. | Communication has been excellent 95% of time with all parties I have been involved with.
14 | 2023-05-09 12:05 | 2023-05-09 15:34 | saara.suvela@helsinkishipyard.fi | Saara Suvela | 4000 |  |  | 4140 Cabin lay-out;4150 Toilet Units; | [5 empty] | KT-teki Vassin, niin meni hyvin. 518 PES-arrangementit tehtiin todella kiireellä muiden työtehtävien lomassa. PES-kuville ei ollut paljon varattua aikaa päivityksiin yms. seuraamiseen. | USPH ja USCG yllätti säännöillään, ei ollut telakalla aiemmista projekteista tuttu (laivaa 516 aiemmista). | KT:n kautta hankinnat, joten ei ollut 420-osastolla sinänsä. Budjetti toki telakalta. KT:n +/- listat yllätti välillä ja osa vaikeasti ennakoitavissa. | PES-kuvat tuntuivat jääneen vähän unholaan. Niiden ylläpitämiseen ei ollut aikaa, ja toisaalta tuntui, että ne eivät olleen enää 3. laivassa ns. niin tärkeässä roolissa (vaikka ehkä olisi pitänyt?) | Henkilöt tuttuja ja toimintatavat muodostuneet jo 516-517 laivoissa, niin kommunikointi oli sinänsä selkeää (vrt. 516 alussa puuttui henkilöitä pyödän toiselta puolelta jne.) Oman osaston henkilöstöä vaihtui paljon 518-laivan puolessa välissä, mikä aiheutta haasteita kommunikaatiossa ja toimintatavoissa, ja sitä kautta asioiden edistymisessä. | Laiva 518 meni edellisten sisaralusten vanavedessä kaiken kaikkiaan. Moni asia jo ratkottu edellisissä, vaikka toki uutta ihmeteltävää oli aina. Esim. pakoteasiat jne. Toimittajat ei suostuneet yhteistyöhön tai oli toimitustaukoja ja toimitushaasteita, jotka hidasti ja vaikeutti projektia.
15 | 2023-05-09 15:28 | 2023-05-09 15:49 | bertrand.frouin@helsinkishipyard.fi | Bertrand Frouin | 5000 |  |  |  | 5710 Water Fire Extinguishing And Deck Washing System; |  |  |  |  | Generally yes. | Rules are fulfilled, no issues with Class. USPH requirements were not clear in first hand. Fulfilled in two steps so not efficiently. It would have been better to add the required features in the very beginning. | final costs within budget, purchase of standard material item is not a very clear process. | - USP requirements (system to incorporate fixed shore connections with back-flow preventers to fulfill USPH rules. The back flow preventer assembly must be complete with isolating valves and test valves to allow testing. This assembly requires space and proper drainage. - Location of fire hydrants needs to be clear. 1 added fire hydrant on deck 2 was built by Almaco on the wrong side of the bulkhead. It would have been necessary to specify a recess on the drawing or move the valve to the accessible side (though it is obvious that a fire hydrant hidden behind a cabin is useless. | Generally no issues. A little more communication during the detail design phase with TK would have prevented the situation described in point above. | Nothing new except for the extended length of the fire zones.
16 | 2023-05-09 15:49 | 2023-05-09 16:11 | bertrand.frouin@helsinkishipyard.fi | Bertrand Frouin | 5000 |  |  |  | 5730 CO2 Fire Extinguishing; |  |  |  |  | Ideally, we should provide a pneumatic release for the EDG to cover the risks when the ship is being restarted. ECR could use water mist with pre-action system as in the wheelhouse, rather than clean agent system. The system is tailored and very sensitive to changes in the piping. We had to re-order nozzles to adjust the system to actual piping layout due to changes done in various phases of the construction (detail design and production). For this reason, system should only be used in a few areas of limited size. | The effect of release on pressure in the protected space hasn't been addressed. Location of the rooms and lack of suitable solutions (with approvals) made it impossible. To be considered for future projects. Otherwise, rules are fulfilled. Class reviewed only supplier's documentation, not shipyard documentation issued for the system. | System was well in budget despite the changes during design and the differences with reference project. Same supplier as in NB516/517. | Changes in the system are first changes versus reference ships. Then, piping arrangement done in detail design in the protected spaces varied from supplier proposed arrangement. As built system varied also from the detail design. In this system, the changes need to be addressed and resulted in necessary adjustments. | System was handled by different persons along the project and this caused a lack of follow-up during some periods of time. Some issues could have been addressed earlier, but without major issues. | System readiness for commissioning was better.
17 | 2023-05-09 16:11 | 2023-05-09 16:33 | bertrand.frouin@helsinkishipyard.fi | Bertrand Frouin | 5000 |  |  |  | 5740 Water Mist Fire Extinguishing System; |  |  |  |  | Generally yes. - For ease of commissioning, a set of test valves (isolating and test valves) should be added for the machinery section valves. - At the location of system main valves, floor drainage should be considered in future projects. - Also treatment of the water storage tanks should be considered in future projects by adding a treatment pump circulating water from the tanks. | No issues in this project. | System final costs are above budget due to an erratic material consumption in all 3 vessels. The budget is mainly exceeded due to the need of creating a material buffer. Eventually, the material usage has been more realistic in NB518 versus 516/517. | Some changes came in relatively late stage from the ceiling design in public spaces (Savi). | Communication with Savi public team has been difficult. Comments sent on their detail design seemed ineffective. Material handling has been a lot better in this project than in 516/517. I used some time reviewing the part list of each area and sent comments to persons in charge of detail design. The similarities with 516/517 helped also. | Some efforts have been paid to make the system ready on time for commissioning (main line readiness, machinery spaces) with a good result. Despite changes in the yard commissioning team, we used less time from Marioff commissioning engineer (excluding the work on transfer voyage). It is difficult to get a large system covering the whole ship ready. It is also important to keep track on the system as a whole, not only piping construction. The system finalization is also totally dependent on the electric connections. | The system covered systems 5720 and 5740.
18 | 2023-05-09 18:05 | 2023-05-09 18:11 | Mikael.Forsman@helsinkishipyard.fi | Mikael Forsman | 9000 | [7 empty] | 9300 Monitoring, Control and Automation;9311 Integrated Automation System (IAS);9318 Light alarms in Engine Spaces;9321 Power Management System (PMS);9333 Emergency Telegraph;9342 Loading Computer; | Yes | No problems | Budget was good, yard was refunded. | First time in 20 years automation design made all drawings, not outsourced. | Machinery design have skilled designers. | Jira and ERM doesn't work as I expected. ACAD without electrical symbols. | More teamwork before purchase of different sister systems.
19 | 2023-05-10 08:12 | 2023-05-10 08:34 | bertrand.frouin@helsinkishipyard.fi | Bertrand Frouin | 5000 |  |  |  | 5750 Foam Fire Extinguishing System; |  |  |  |  | The system as built could have been a little better with a better follow-up (change of system responsible person) | There was no rules clearly defining the need and requirements for this system. But it was not a challenge. Proposed solution was already accepted in reference ships. Approval of the system by Class was done only on the base of supplier's documentation. Approval came late due to failure of the supplier to submit documentation to Class. Luckily no issue came up from approval. | System was purchased from MINIMAX who has been supplying the Clean agent system in all 3 shios of Vega series. Tyco was the supplier for 516/517. The reason for change was only to get a better price for both systems. | Some comments related to the arrangement of the room where equipment is located came on a late stage from Owner. Some improvements were made versus previous ships in this regards. The comments were related to having a drip tray around the system equipment. This was not addressed in any other design and should have been addressed earlier. That kind of items (drip trays under equipment and their drainage arrangement) needs to be better coordinated in future projects. | Change of system responsible designer during the project made so that, there was a lack of communication and follow-up during the detail design phase. No critical issues finally but the nozzle arrangement, for example, could have been better if feedback had been given to the detail designer when asked. | System was a little different due to change of supplier. Better arrangement around the system equipment was provided. One drain valve which was located outside in NB516/517 was not provided in NB518 and was commented in a late stage by Owner. The saving was not significant and the valve was useful. However, it was not added when requested by Owner due to the timing of their request.
20 | 2023-05-10 08:34 | 2023-05-10 09:21 | bertrand.frouin@helsinkishipyard.fi | Bertrand Frouin | 5000 |  |  |  | 5790 Fire Fighting Equipment;5730 CO2 Fire Extinguishing; |  |  |  |  | We should provide a little bit more portable extinguishers. in this type of ships. | Rules are fulfilled but when NB518 left, the signage was still missing in many places. For a proper readiness of the fire control plan items, the ship needs to be fully ready. This was inspected by Class and approved but there will be more inspections, for example by USCG. Situation was better in NB517 where all these inspections were carried out before the ship left teh shipyard. | Items were purchased on time. Delivery was a little late due to invoice payment issues. However, it was without consequences due to delays in the project. Purchases were within budget. | First revision of the drawing was late. Class used this document to comment on general safety related issues as this gives an overview of safety on board. First approved revision was revision C. When preparing updated revision due to change of flag. Many items inaccurate were found. Also changes in GA plan needed to be addressed. Elaboration of this document is requiring more work than it looks because information is presented and categorized in a different way than on dedicated system drawings. Level of details required is not always available in other basic design documentation. Drawing released early can receive an approval in principle. However, the drawing needs a lot of work in late phase to bring some accuracy and show exact location of equipment and devices on board. The difficult situation related to the fact that the ship left the shipyard unfinished was partly compensated by the good work and effort paid during the last 2 weeks to get the material installed on board. However, readiness for these items could have been achieved earlier in machinery spaces which were not late. | The communication and cooperation has been really good in the last run to make the AS BUILT drawing ready and inspection succeed. | Situation was not as bad as in NB516 where the ship's departure was not so well anticipated. In NB517, due to the change in contract, the ship stayed longer at the shipyard than expected. This added time allowed to reach the necessary completion and readiness for a successful inspection of the fire control plan items. In NB518, the ship was not ready enough, but anticipation of the ship's departure, even though not ready helped to provide a better level than in NB516. Also the failures noticed in NB517 (missing material, wrong information...) were anticipated and corrected in NB518.
21 | 2023-05-10 10:41 | 2023-05-10 11:14 | outi.lehtimaki@helsinkishipyard.fi | Outi Lehtimaki | 5000 |  |  |  | 5610 Air Conditioning in Interior Spaces; |  |  |  |  | Because "cousin ship" all design material was not added into Kronodoc under NB518 because it was assumed that same persons continue from NB516-517 and they are already familiar with material | Air balancing report for future USPH inspections is missing from Kronodoc. | "Real" delivery control still missing. Who is in charge of TK extra prices (mainly work); approving, doing TMR and who will do final PO. | Heat load calculation "as built" version not useful; updated info in AC plans and balancing | Change of system responsible person was not informed to all parties and questions were presented to "old one". Valid contact info was not available in Kronodoc. TK organisation was total mess, too many persons involved and roles unknown. | Picking without part list was reduced compared to NB516-517 which was good thing. | TRI / final inspection of AC rooms might be useful; has been earlier, but it was agreed during NB516 that not needed. How we confirm that all background installation done and inspected and also AC commissiong/adjustment is done before ceiling is closed ?
22 | 2023-05-10 15:46 | 2023-05-10 16:00 | joni.korpisola@helsinkishipyard.fi | Joni Korpisola | 4000 |  |  | 4510 Insulation; | [5 empty] | Yes | It's a bit unclear if A-15 fire insulation needs overlaps. In 518 the shipowner wanted to have overlaps around pipes (penetrating A-15 bulkhead). | Budget was exceeded, material prices had risen a lot from 516 (from year 2021) | When insulation contractor suggest's changes in drawing (scheme of insulation), it's important to check the cost effect for shipyard. | Co-operation was good between contractor, production insulation foreman and design. | No difference | Pins for insulation were installed too late - was planned to be installed in block factory, but quite much was installed in blocks or onboard after painting.
23 | 2023-05-11 13:10 | 2023-05-11 13:22 | Leena.Yli-Nikkila@helsinkishipyard.fi | Leena Yli-Nikkilä | 9000 | [7 empty] | 9132 Main Switchboards (MS11_MS12_MS21_MS22);9133 Emergency Switchboards (ES1_ES2_ES3);9134 Distribution Boards (PB_LB_HB_OB_etc.);9135 Motor Starter Units and Separate Starters;9136 Shore connection (SC1);9114 Emergency Diesel Generator; | Kymys ei täysin ymmärretävä, tarkoitetaanko tällä sitä miten sähkö on onnistunut? | Omien järjestelmien osalta (sähkönjakelu) vaikuttaa moneen järjestelmään säännöt esim. tarpeet tuplasyötöistä, syötönvaihdot jne. Yleistä kommenttia: säännöistä kaivataan yksityiskohtaista opastusta, esim. koulutusta. Voisiko järjestää esim. sisäistä kurssitusta jotta sähköllä osataan ottaa huomiota sääntökohdat esim. veljes/sisarjärjestöjen kanssa yhdessä. | tarjouspyynnöt ja tarjouskierros monimutkainen ja aikaa vievä prosessi. Kaikkiaan kun saadaan 3 tarjousta sen jälkeen alkaa uusi tinkauskierros jossa taas hintaa lasketaan. Kun on päästy loppusuoralle asiat on jo muuttuneet. (Esim. tullut uusia sähkönkuluttajia tai uutta tietoa). Logistiikka ja tuotteiden oikea aikataulutus on haasteellinen, aikataulut eivät päde tai sitten tavarat ovat llian aikaisin telakalla. Kustannuksia ja haasteita säilyttämiseen Budjetin seuranta, vastuut kenelle kuuluu budjettiseuranta? Tavaroiden tulemisen viivästyminen joko toimittajasta tai telakasta johtuen. Nk. toimitusvalvonta puuttuu tällä hetkellä kokonaan. Osto ei seuraa tulevatko tavarat silloin kuin pitäisi tulla. Kuormittaa suunnittelua runsaasti jos asiat ei mene kuten pitäisi. | PES sähkön osalta kannattaisi tehdä telakan omalla väellä. 518 tehtiin Kroatiassa jossa oli paljon virheitä ja niitä jouduttiin sitten VAS-suunnittelussa korjaamaan ja paikkaamaan. Pitää selvittää alihankkijan kyky toimittaa taatusti laadukasta työtä jota ei telakka sitten joudu parsimaan kasaan uudestaan. Aina halvalla suunnittelutoimistolla esim. KT ei ole ollenkaan omaa sähkösuunnittelua vaan he tilaavat sen jostain ulkopuolelta. Tässä on monta liikkuvaa osaa jotka pitää korjata ja rikkinäinen puhelin -ongelma. Tarvitaan parempaa koordinointia ja aikaa telakalla valvoa KT ja muita alihankkijoita. | Suunnittelua tehdään samaan aikaan monella osastolla, eli siinä vaiheessa kun telakan pitää jo löydä lukkoon sähkön jakelun keskukset ei vielä ole tarpeeksi lähtötietoja mitä ollaan ostamalla muilla osastoilla. Muutokset vaatisivat tarkempaa muutoshallintaa ja kertomista eri osastoiden välillä. Eli tarvitsee olla vaikka työryhmät, jossa olisi myös aina sähkö mukana. Harva laite toimii ilman sähköä ja sitä ei tarpeeksi ole otettu huomioon suunnittelussa. | protolaivat olivat vaikeita tehdä, mutta kyllä niistä opittiin. Osaa asioista ei saatu enää muutettua joten mentiin samalla tavalla kuin edellisissäkin